## Power
			Development			Tests		App					Complete				By Calculator Progress				By Section Progress
Module	Calculator	Calculates	Coded	Arguments Checked	Docstring Written	Written	Passed	Form	Backend	Arguments Explained	Calculator Explain	Docs	Tested	Development	Tests	App	Overall	Competed	Remaining	Percent Complete		Section	Task	Y	N	Percent Complete	Total
Means	One Sample	Equality (Known SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%		Development	Coded	89	39	70%	128
Means	One Sample	Equality (Unknown SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Arguments Checked	89	39	70%	128
Means	One Sample	Superiority (Known SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Docstring Written	86	42	67%	128
Means	One Sample	Superiority (Unknown SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Section Complete	86	42	67%	128
Means	One Sample	Equivalence (Known SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Total Tasks	264	120	69%	384
Means	One Sample	Equivalence (Unknown SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%		Tests	Written	85	43	66%	128
Means	Two Sample (Parallel)	Equality (Known SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Passed	85	43	66%	128
Means	Two Sample (Parallel)	Equality (Unknown SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Section Complete	85	43	66%	128
Means	Two Sample (Parallel)	Superiority (Known SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Total Tasks	170	86	66%	256
Means	Two Sample (Parallel)	Superiority (Unknown SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%		App	Form	0	128	0%	128
Means	Two Sample (Parallel)	Equivalence (Known SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Backend	0	128	0%	128
Means	Two Sample (Parallel)	Equivalence (Unknown SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Arguments Explained	0	128	0%	128
Means	Two Sample (Crossover)	Equality (Known SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Calculator Explain	0	128	0%	128
Means	Two Sample (Crossover)	Equality (Unknown SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Docs	0	128	0%	128
Means	Two Sample (Crossover)	Superiority (Known SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Tested	0	128	0%	128
Means	Two Sample (Crossover)	Superiority (Unknown SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Section Complete	0	128	0%	128
Means	Two Sample (Crossover)	Equivalence (Known SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%			Total Tasks	0	768	0%	768
Means	Two Sample (Crossover)	Equivalence (Unknown SD)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%		Overall	Complete	0	128	0%	128
Means	One-Way ANOVA	Pairwise Comparisons	Y	Y	Y	N	N	N	N	N	N	N	N	Y	N	N	N	3	2	60%		Total		434	974	31%	1408
Means	One-Way ANOVA	Simultaneous Comparisons	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Means	Multiple-Sample Williams	Equality	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%		Calculators Part	67.81%
Means	Multiple-Sample Williams	Superiority	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Means	Multiple-Sample Williams	Equivalence	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	One Sample	Equality	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	One Sample	Superiority	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	One Sample	Equivalence	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Two Sample (Parallel)	Equality	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Two Sample (Parallel)	Superiority	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Two Sample (Parallel)	Equivalence	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Two Sample (Crossover)	Equality	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Two Sample (Crossover)	Superiority	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Two Sample (Crossover)	Equivalence	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	One-Way ANOVA	Pairwise Comparisons	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Williams Design	Equality	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Williams Design	Superiority	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Williams Design	Equivalence	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Relative Risk (Parallel)	Equality	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Relative Risk (Parallel)	Superiority	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Relative Risk (Parallel)	Equivalence	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Relative Risk (Crossover)	Equality	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Relative Risk (Crossover)	Superiority	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Large Sample)	Relative Risk (Crossover)	Equivalence	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Exact)	Binomial	Equality	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Proportions (Exact)	Fisher's Exact Test	Equality	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Proportions (Exact)	Optimal Multiple-Stage Designs	Optimal Two-Stage Design	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Proportions (Exact)	Optimal Multiple-Stage Designs	Flexible Two-Stage Design	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Proportions (Exact)	Optimal Multiple-Stage Designs	Optimal Three-Stage Design	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Goodness of Fit	Tests of Goodness of Fit	Pearson's Test	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Goodness of Fit	Test of Independance (Single Strata)	Pearson's Test	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Goodness of Fit	Test of Independance (Single Strata)	Likelihood Ratio Test	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Goodness of Fit	Test of Independance (Multiple Strata)	Cochran-Mantel-Haenszel Test	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Goodness of Fit	Test of Categorical Shift	McNemar's Test	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Goodness of Fit	Test of Categorical Shift	Stuart-Maxwell Test	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Goodness of Fit	Carry Over Test	Carry Over Test	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Time To Event	Exponential Model	Equality	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Time To Event	Exponential Model	Superiority	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Time To Event	Exponential Model	Equivalence	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Time To Event	Cox's Proportional Hazard Model	Equality	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Time To Event	Cox's Proportional Hazard Model	Superiority	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Time To Event	Cox's Proportional Hazard Model	Equivalence	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Time To Event	Weighted Log-Rank Test	Tarone Ware	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Group Sequential Methods	Group Sequential Methods	Pocock's Test	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Group Sequential Methods	Group Sequential Methods	O'Brian Fleming's Test	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Group Sequential Methods	Group Sequential Methods	Wang and Tsiatis' Test	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Group Sequential Methods	Group Sequential Methods	Inner Wedge Test	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Group Sequential Methods	Group Sequential Methods	Binary Variables	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Group Sequential Methods	Group Sequential Methods	Time To Event Data	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Group Sequential Methods	Group Sequential Methods	Alpha Spending Function	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Group Sequential Methods	Group Sequential Methods	Sample Size Re-Estimation	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Group Sequential Methods	Group Sequential Methods	Conditional Power for Means	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Group Sequential Methods	Group Sequential Methods	Conditional Power for Proportions	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Variablility	Intra-subject Variablilites	Parallel Design with Replicates (Equality)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Intra-subject Variablilites	Parallel Design with Replicates (Superiority)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Intra-subject Variablilites	Parallel Design with Replicates (Similarity)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Intra-subject Variablilites	Replicated Crossover Design (Equality)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Intra-subject Variablilites	Replicated Crossover Design (Superiority)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Intra-subject Variablilites	Replicated Crossover Design (Similarity)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Intra-subject CVs	Simple Random Effects Model (Equality)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Intra-subject CVs	Simple Random Effects Model (Superiority)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Intra-subject CVs	Simple Random Effects Model (Similarity)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Intra-subject CVs	Conditional Random Effects Model (Equality)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Intra-subject CVs	Conditional Random Effects Model (Superiority)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Intra-subject CVs	Conditional Random Effects Model; (Similarity)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Inter-subject Variablilites	Parallel Design with Replicates (Equality)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Inter-subject Variablilites	Parallel Design with Replicates (Superiority)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Inter-subject Variablilites	Replicated Crossover Design (Equality)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Inter-subject Variablilites	Replicated Crossover Design (Superiority)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Total Varaibility	Parallel Design without Replicates (Equality)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Total Varaibility	Parallel Design without Replicates (Superiority)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Total Varaibility	Parallel Design without Replicates (Similarity)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Total Varaibility	Parallel Design with Replicates (Equality)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Total Varaibility	Parallel Design with Replicates (Superiority)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Total Varaibility	The Standard 2 × 2 Crossover Design (Equality)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Total Varaibility	The Standard 2 × 2 Crossover Design (Superiority)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Total Varaibility	Replicated 2 × 2m Crossover Design (Equality)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Variablility	Total Varaibility	Replicated 2 × 2m Crossover Design (Superiority)	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Bioequivalence Testing	Bioequivalence Testing	Average Bioequivalence	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Bioequivalence Testing	Bioequivalence Testing	Population Bioequivalence	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Bioequivalence Testing	Bioequivalence Testing	Individual Bioequivalence	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Bioequivalence Testing	Bioequivalence Testing	In-Vitro Bioequivalence	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Dose Response	Continuous Response	Linear Contrast Test	Y	Y	Y	Y	Y	N	N	N	N	N	N	Y	Y	N	N	5	0	100%
Dose Response	Binary Response	Binary Response	Y	Y	Y	N	N	N	N	N	N	N	N	Y	N	N	N	3	2	60%
Dose Response	Time to Event	Time to Event	Y	Y	Y	N	N	N	N	N	N	N	N	Y	N	N	N	3	2	60%
Dose Response	Williams Test for Minimum Effective Dose	Williams Test for Minimum Effective Dose	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Dose Response	Cochran-Armitage's Test for Trend	Cochran-Armitage's Test for Trend	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Dose Response	Dose Escalation Trials	A + B Design without Dose Deescalation	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Dose Response	Dose Escalation Trials	A + B Design with Dose Deescalation	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Microarray Studies	FDR Control	FDR Control	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Microarray Studies	FWER Control	FWER Control	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Bayesian Sample Size	Bayesian Sample Size	One Sample Known Precision	Y	Y	Y	N	N	N	N	N	N	N	N	Y	N	N	N	3	2	60%
Bayesian Sample Size	Bayesian Sample Size	One Sample Unknown Precision	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Bayesian Sample Size	Bayesian Sample Size	One Sample Mixed Bayesian Likelihood	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Bayesian Sample Size	Bayesian Sample Size	Two Sample Known Common Precision	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Bayesian Sample Size	Bayesian Sample Size	Two Sample Unknown Common Precision	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Bayesian Sample Size	Bayesian Sample Size	Two Sample Known Unequal Precision	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Bayesian Sample Size	Bayesian Sample Size	Two Sample Unknown Unequal Precision	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Nonparametric Methods	One Sample Location	One Sample Location	Y	Y	N	Y	Y	N	N	N	N	N	N	N	Y	N	N	4	1	80%
Nonparametric Methods	Two Sample Location	Two Sample Location	Y	Y	N	Y	Y	N	N	N	N	N	N	N	Y	N	N	4	1	80%
Nonparametric Methods	Test for Independance	Test for Independance	Y	Y	N	Y	Y	N	N	N	N	N	N	N	Y	N	N	4	1	80%
Other Areas	QT/QTc Studies with Time-Dependant Replicates	Parallel Group Design	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Other Areas	QT/QTc Studies with Time-Dependant Replicates	Crossover Design	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Other Areas	Propensity Analysis in Non-Randomized Studies	Weighted Mantel-Haenszel	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Other Areas	Repeated Measures ANOVA	Repeated Measures ANOVA	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Other Areas	Quality of Life Studies	Quality of Life Studies	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Other Areas	Bridging Studies	Assesment of Similarity	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Other Areas	Vaccine Clinical Trials	Reduction in Disease Incidence	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Other Areas	Vaccine Clinical Trials	Evaluation of Vaccine Efficacy with Extremely Low Disease Incidence	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%
Other Areas	Vaccine Clinical Trials	Composite Efficacy Measure	N	N	N	N	N	N	N	N	N	N	N	N	N	N	N	0	5	0%

## Power_extra
Task No.	Description	Complete	Notes
1	Add support for different sds in two sample means calculator.
2	Add ability to select unknown and not rely on what is `None`.
3	Add ability to choose \sigma_{m} or \sigma_{d} as desired. \sigma_{m} = 2*\sigma_{d}. PASS uses \sigma_{d}.
4	Review all docstrings (esp wrt definitions)
5	Change stdev references to sigma
6	Add docstrings to all class methods and functions
7	Change binomial API from p, p_0 to p_0, p_1 as per Chen
8	Put bounds on alpha and beta to ensure bad values are not generated. If a value is out of bounds, recalculate the others as appropriate.
9	Check how power and alpha are searched for when unknown for the Multi-Williams Design
10	Check Exponential Formula; Chow seems to be wrong
11	Check Average Bioequivalence Formula; Chow seems to be wrong
12	Review all parameter checks
13	Verify all directions of 'margin' (esp. one-sample means)
14	Get unified form for docstrings
15	Add loss to follow-up, etc to Exponential Time To Event Model (7.2.5 in Chow)

## App
Task No.	Description	Complete	Notes
1	Add sphinx support for documentation
2	Add stripe support
3	Add user accounts
4	Tie user accounts to stripe payments
5	Add payment options page
6	Add email subscription for updates (Drip)		www.getdrip.com
7	Add save feature for calculators
8	Add interface for users to access saved results
9	Add export to csv for results
10	Add export to pdf for results
11	Add export to word for results
12	Add loading image between calculator and results		See: http://bradsknutson.com/blog/display-loading-image-while-page-loads/
13	Form Validation (Client Side)		See: http://foundation.zurb.com/docs/components/abide.html
14	Form Validation (Server Side)
15	Data Model
16	About Page
17	Contact Page

## Deployment
Task No.	Description	Complete	Notes
1	Get Domain	X	study-design.io registered with Gandi.net
2	Get AWS account	X
3	Get Stripe account	X
4	Setup AWS
5	Create deploy script to AWS
6	Create control script for AWS
7	Update CNAME
8	Deploy
9	Move Stripe Status to Active

## Marketing
Task No.	Description	Complete	Notes
1	Announce on Data Tau
2	Announce on Louden Analytics
3	Add to Github profile
4	Add to Stack Overflow profile
5	Announce on Hacker News
6	Announce on appropraite sub-reddits
7	Research Drip
8	Sign up for Drip

## Misc
Task No.	Description	Complete	Notes
1	Cleanup code
2	Open source Power
3	Open source Randomization	X	See github.com/louden/randomization